BLISS PALM BAY

Site Plan Feasibility Report

2165 Sandy Pines Drive NE, Palm Bay, FL 32905

Parcel ID: 28-37-27-00-7  |  BCPAO Account: 2835546

Prepared for: The Property Squad, Inc.

Prepared by: Everest Capital USA

Date: February 6, 2026

Project ID: SPD-2025-002

Status: HOLD PENDING PUD REVIEW

# Table of Contents

Executive Summary

Section 1: Property Overview

Section 2: Zoning & Land Use

Section 3: Site Analysis

Section 4: Environmental Constraints

Section 5: Infrastructure & Utilities

Section 6: Traffic & Access

Section 7: HOA & CC&R Analysis

Section 8: Development Scenarios

Section 9: Cost Estimate

Section 10: Permit Roadmap

Section 11: Risk Matrix

Section 12: Recommendation

# Executive Summary

RECOMMENDATION: HOLD / CONDITIONAL NO-GO

This feasibility report evaluates a proposed multifamily development on a 1.114-acre vacant parcel at 2165 Sandy Pines Drive NE, Palm Bay, Florida. The parcel is zoned PUD (Planned Unit Development) with a High Density Residential (HDR) future land use designation, theoretically supporting up to 20 dwelling units per acre (22 units maximum).

Key Metrics:

Land Value: $55,000 (BCPAO 2025 market value)

Acquisition Price: $35,100 (tax deed, July 2023)

Gross Area: 1.114 acres (48,516 SF) per survey traverse calculation

Net Buildable (3-story): 11,325 SF (23.3%) after wellhead easement + setbacks

Maximum Density: 22 units gross / 11 units net (after easement reduction)

Environmental Costs: $77,000 - $203,000 (1.4x to 3.7x land value)

Total Development Cost: $3.79M (11 units) / $7.26M (22 units)

Financial Feasibility: NOT FEASIBLE — development cost exceeds stabilized value by ~2x

Five Critical Constraints Identified:

1. HOA CC&Rs (POTENTIAL FATAL): Sandy Pines Preserve is a gated community of exclusively 1-2 story single-family homes. CC&Rs almost certainly prohibit 3-4 story multifamily construction.

2. No Sewer/Water Available (HIGH): Palm Bay GIS confirms no sewer or water service at parcel. Sewer extension required at developer cost.

3. FEMA Zone A Flood (HIGH): Entire parcel in Special Flood Hazard Area with no BFE determined. Flood study required ($5K-$25K).

4. NWI Wetland PEM1Cd (HIGH): 10.3-acre freshwater emergent wetland envelops parcel. Mitigation credits: $40K-$100K.

5. Wellhead Protection (HIGH): 200-ft radius easement covers 47% of parcel. No construction in easement zone for ~10 years.

The combination of five overlapping constraints makes multifamily development economically infeasible at current market conditions. Environmental compliance costs alone ($77K-$203K) exceed the land value ($55K). Total development cost for an 11-unit project ($3.79M) is approximately double the stabilized property value ($1.93M at a 6% cap rate). The project should be placed on HOLD pending CC&R retrieval and PUD ordinance review. If CC&Rs prohibit multifamily, the project should be KILLED for the intended use.

# Section 1: Property Overview

Location & Legal Description

| Field | Value |
| --- | --- |
| Address | 2165 Sandy Pines Drive NE, Palm Bay, FL 32905 |
| Parcel ID | 28-37-27-00-7 |
| BCPAO Account | 2835546 |
| Legal Description | E 1/2 of S 1/2 of NE 1/4 of Section 27, T28S, R37E, less E 83 ft |
| Plat References | PB 32/78, ORB 3636/2327, ORB 3731/2000 |
| Jurisdiction | City of Palm Bay, Brevard County, Florida |
| Millage Code | 34U0 (Palm Bay) |

Ownership

| Field | Value |
| --- | --- |
| Current Owner | The Property Squad, Inc. |
| Owner Type | Florida Corporation |
| Mailing Address | 390 Roosevelt Ave, Satellite Beach, FL 32937 |
| Acquisition Date | July 24, 2023 |
| Acquisition Price | $35,100 |
| Deed Type | Tax Deed (XD) — Book 9844, Page 0688 |
| 2025 Market Value | $55,000 |
| 2025 Taxable Value | $55,000 |
| Property Use Code | 0008 — Vacant Residential (Multi-Family, Unplatted) |
| Total Buildings | 0 (vacant land) |

Sales History

| Date | Price | Deed Type | Recording |
| --- | --- | --- | --- |
| 07/24/2023 | $35,100 | Tax Deed (XD) | Book 9844/Page 0688 |
| 06/30/2011 | $4,300 | Tax Deed (XD) | Book 6419/Page 1735 |
| 10/29/2004 | $277,000 | Trustee Deed (TD) | Book 5382/Page 2335 |

Note: Two consecutive tax deed sales (2011 and 2023) indicate long-term vacancy. The $277K-to-$35K price decline reflects the severe constraints on this parcel, not general market conditions.

# Section 2: Zoning & Land Use

Current Zoning Designation

| Field | Value |
| --- | --- |
| Current Zoning | PUD (Planned Unit Development) |
| Future Land Use | HDR (High Density Residential) |
| Maximum Density (HDR) | Up to 20 du/acre |
| PUD Type | Small PUD (SPUD) — min 1.0 acre (Section 185.061) |
| PUD Ordinance | NOT YET OBTAINED — must request from City Clerk |
| Zoning Source | Palm Bay GIS REST — live query Feb 6, 2026 |

PUD Zoning Implications

PUD zoning means development standards (setbacks, height, density, permitted uses) are controlled by the approved PUD ordinance and development plan — NOT by the standard RM district tables in the municipal code. The PUD ordinance for Sandy Pines Preserve has not been located through online searches. It must be obtained from the Palm Bay City Clerk. Without this document, no definitive feasibility determination can be made.

RM-15 Reference Standards (Fallback Benchmark)

Since the PUD ordinance is unavailable, RM-15 standards are used as a reference benchmark. RM-15 is the most comparable standard zoning district for HDR future land use:

| Standard | Requirement |
| --- | --- |
| Maximum Density | 15 du/acre |
| Front Setback | 25 ft OR building height, whichever is greater |
| Side Setback | 15 ft OR building height, whichever is greater |
| Rear Setback | 25 ft OR building height, whichever is greater |
| Max Building Height | 40 ft |
| Building Separation | 30 ft |
| Parking Setback | 10 ft from property line |
| Open Space | 25% of gross site area (PUD requirement, Section 173.070) |

Ordinance 2024-45 (Nov 7, 2024): All RM-10 districts rezoned to RM-15 citywide (361 acres affected). This ordinance does NOT apply to PUD-zoned parcels.

# Section 3: Site Analysis

Survey-Verified Dimensions

Source: Smith Survey Company (L.B. 7436), Scale 1" = 30'

| Boundary | Bearing | Distance | Adjacent |
| --- | --- | --- | --- |
| North Boundary | S89°31'14"E | 200.00 ft | Adjacent to Tract D (Preserve) |
| East Boundary | S00°28'46"W | 277.15 ft | Adjacent to Tract O (Preserve) |
| South (Sandy Pines Dr) | Curve R=1036.12' | 214.67 ft (arc) | Road frontage (curved) |
| West Boundary | N00°28'46"E | 200.00 ft | Adjacent to Tract D (Preserve) |

Area Calculations

| Source | Square Feet | Acres |
| --- | --- | --- |
| Computed Area (traverse) | 48,516 SF | 1.114 acres |
| GIS Area | 48,424 SF | 1.11 acres |
| BCPAO Recorded | 47,916 SF | 1.10 acres |
| Perimeter | 891.82 ft | (GIS = computed) |

Buildable Area Analysis

| Description | Square Feet | Acres | % of Parcel |
| --- | --- | --- | --- |
| Total Parcel | 48,516 | 1.114 | 100% |
| Wellhead Easement | 22,803 | 0.524 | 47% |
| Net (excl. wellhead) | 25,713 | 0.590 | 53% |
| Net after setbacks (2-story, 25ft) | 14,555 | 0.334 | 30.0% |
| Net after setbacks (3-story, 35ft) | 11,325 | 0.260 | 23.3% |
| Net after setbacks (4-story, 40ft) | 9,861 | 0.226 | 20.3% |

Wellhead Protection Easement

A 200-foot radius circular easement around a City of Palm Bay public water supply well covers the western 47% of the parcel (22,803 SF). Per Florida DEP Chapter 62-521 FAC, no new construction, impervious surfaces, or regulated substance storage is permitted within this zone. Surface parking may be allowed (survey annotates "PARKING" in this area). The well may be decommissioned in ~10 years per Palm Bay Utilities (Tim Roberts, Sept 11, 2025).

# Section 4: Environmental Constraints

FEMA Flood Zone

| Item | Detail |
| --- | --- |
| Flood Zone | A (Special Flood Hazard Area) |
| SFHA | Yes — 1% annual chance (100-year) flood |
| Base Flood Elevation | NOT DETERMINED (Study Type: NP) |
| DFIRM ID | 12009C |
| CRS Rating | 7 (15% flood insurance discount) |
| Flood Study Cost | $5,000 - $25,000 (HEC-RAS hydraulic modeling) |

The entire parcel is in FEMA Zone A with no published Base Flood Elevation. The developer must commission a hydraulic study (HEC-RAS modeling) to establish BFE before any building design can proceed. All habitable floors must be elevated above BFE plus 1 foot minimum freeboard per Florida Building Code.

National Wetlands Inventory (NWI)

| Item | Detail |
| --- | --- |
| NWI Code | PEM1Cd |
| Type | Freshwater Emergent Wetland |
| Feature Total | 10.316 acres (parcel within larger polygon) |
| Classification | Palustrine, Emergent, Persistent, Seasonally Flooded, Partially Drained |
| Delineation Cost | $3,000 - $8,000 |
| Mitigation Credits | 0.3-0.5 UMAM credits at $125K-$200K/credit |
| Mitigation Cost | $40,000 - $100,000 |
| Primary Bank | Farmton Mitigation Bank (south Brevard service area) |

Listed Species

Palm Bay has an active USFWS-approved Habitat Conservation Plan (HCP) covering Florida Scrub-Jay, Eastern Indigo Snake, and Gopher Tortoise. The HCP scrub-jay fee is $125 per quarter-acre ($560 total). A 100% gopher tortoise survey is required before any land clearing. Wood stork foraging habitat (PEM1Cd wetland type) may trigger USFWS consultation.

Environmental Cost Summary

| Item | Low Estimate | High Estimate |
| --- | --- | --- |
| Flood study / BFE determination | $5,000 | $25,000 |
| Elevation certificates (3x) | $500 | $6,000 |
| Wetland delineation | $3,000 | $8,000 |
| Listed species surveys | $2,000 | $8,000 |
| Environmental consultant (ERP) | $15,000 | $40,000 |
| SJRWMD ERP application fee | $9,000 | $9,000 |
| Wetland mitigation credits | $40,000 | $100,000 |
| Gopher tortoise survey/relocation | $1,500 | $6,000 |
| Scrub-jay HCP fee | $560 | $560 |
| TOTAL | $76,560 | $202,560 |

Environmental costs ($77K-$203K) represent 139%-368% of the land value ($55K). Wetland mitigation credits are the single largest cost component at $40K-$100K.

# Section 5: Infrastructure & Utilities

| Utility | Provider | Available | Notes |
| --- | --- | --- | --- |
| Water | City of Palm Bay (PBUD) | NO* | Wellhead within 200ft but no main at property line |
| Sewer | City of Palm Bay (PBUD) | NO | Not in SANC/WANC phase. Extension required. |
| Electric | FPL | YES | Serves all Brevard County |
| Natural Gas | Florida City Gas | LIKELY | Address-specific confirmation needed |
| Stormwater | MTWCD / Palm Bay | N/A | On-site system required. MTWCD permit required. |
| Cable/Internet | Spectrum | YES | 100% coverage, up to 1 Gbps |

* Water Availability Paradox: Despite a city wellhead within 200 feet, Palm Bay GIS designates this parcel as Water_Avail: NO. The wellhead is a raw water production well feeding a treatment plant, not the distribution system. A water main may not extend to this parcel's frontage.

Sewer Extension Analysis

Adjacent parcels (2153, 2240, 2260, 2300 Sandy Pines Dr) have both water and sewer available, suggesting the sewer main runs along Sandy Pines Drive but does not extend to this parcel's frontage. Sewer extension cost is estimated at $50-$100 per linear foot. Distance to nearest main is unknown but may be at 2153 Sandy Pines Dr (adjacent parcel).

Impact Fees

| Fee Category | Amount |
| --- | --- |
| Palm Bay Water | $2,221/unit |
| Palm Bay Sewer | $3,544/unit |
| Brevard County Transportation | $2,381/unit (3+ story) |
| Brevard County Education | $1,941/unit |
| Brevard County Other | $1,750/unit (est.) |
| Total per Unit | $11,837/unit |
| Total (11 units) | $130,207 |
| Total (22 units) | $260,414 |

# Section 6: Traffic & Access

Road Network

Sandy Pines Drive NE is a PRIVATE road within the Sandy Pines Preserve gated community. All traffic from the proposed development must pass through the community's security gate and HOA-controlled roads before reaching Malabar Road (SR 514).

ITE Trip Generation (LU 221 — Mid-Rise Multifamily)

| Scenario | Daily Trips | AM Peak | PM Peak |
| --- | --- | --- | --- |
| 11-unit scenario | 50 ADT | 4 | 4 |
| 22-unit scenario | 100 ADT | 8 | 9 |

Both scenarios generate well below 100 peak-hour trips, which is the common Florida threshold for requiring a formal Traffic Impact Study (TIS). The project's impact on Malabar Road (SR 514) is de minimis at 0.3-0.6% of corridor volume.

Malabar Road (SR 514) Conditions

Current: 16,000 AADT on a 2-lane undivided road — severely congested

Widening: FDOT PD&E completed May 2018 — widen to 4-lane divided ($84M-$97M). NOT FUNDED.

Safety: 56% increase in crashes over 5 years

Private Road / HOA Considerations

HOA Board approval required for any change in use or increased traffic

Road maintenance contribution agreement likely needed

Emergency vehicle access must be verified with Palm Bay Fire-Rescue

Construction traffic access through gated community requires HOA coordination

# Section 7: HOA & CC&R Analysis

WARNING: POTENTIAL FATAL CONSTRAINT

Community Profile

| Item | Detail |
| --- | --- |
| Community | Sandy Pines Preserve |
| Type | Gated community with security access |
| Year Built | 1998-2003 |
| Housing Types | Single-family detached + townhomes (1-2 story only) |
| Multifamily Buildings | NONE exist anywhere in community |
| HOA Fee (Phase 1&2) | $246/quarter (~$82/month) |
| Median Sale Price | $268,250 (Phase 1&2) |

HOA Governance Structure

| Phase | Management | Phone | Sunbiz Filing |
| --- | --- | --- | --- |
| Phases 1 & 2 | Leland Management | (407) 447-9955 | N97000006305 |
| Phases 3 & 4 | Artemis Lifestyles | N/A | N01000002407 |
| Courtyards | Sentry Management | (407) 788-6700 | N99000003017 |

Multifamily Feasibility Under CC&Rs

Based on extensive research, multifamily construction (3-4 story apartment buildings) is ALMOST CERTAINLY PROHIBITED by the Sandy Pines Preserve CC&Rs. Evidence includes:

All existing structures across all phases are exclusively 1-2 story single-family and townhome

HOA incorporated under FL Chapter 720 (Homeowners Association Act)

No apartments, condos, or multifamily buildings exist anywhere in the community

Typical late-1990s gated community CC&Rs restrict to single-family/townhome use types

Architectural Review Committee (ARC) approval almost certainly required

CC&R Status:

The CC&Rs are recorded in OR Book 3636, Page 2327 at the Brevard County Clerk. They have NOT yet been obtained or reviewed. This is the SINGLE MOST CRITICAL action item. If CC&Rs prohibit multifamily and cannot be amended (typically requires 75% supermajority vote), the project is NOT VIABLE for the intended use.

# Section 8: Development Scenarios

Scenario A: 11-Unit (Net Buildable Density)

| Parameter | Value |
| --- | --- |
| Units | 11 |
| Building Configuration | Single 3-story building (~4,333 SF footprint) |
| Building Zone | Eastern portion of parcel (outside wellhead easement) |
| Net Buildable Area | 11,325 SF (0.260 acres) after setbacks + easement |
| Average Unit Size | 900 SF |
| Parking | 22 surface spaces in wellhead easement zone (west portion) |
| Open Space | Wellhead zone remainder (~12,700 SF) as passive recreation |
| Estimated Cost | $3,786,326 ($344,211/unit) |

Scenario B: 22-Unit (Maximum Gross Density)

| Parameter | Value |
| --- | --- |
| Units | 22 |
| Building Configuration | Two 4-story buildings (~3,063 SF footprint each) |
| Building Zone | Full parcel (requires wellhead easement resolution) |
| Net Buildable Area | 9,861 SF per building zone after 40-ft setbacks |
| Average Unit Size | 850 SF |
| Parking | 44 surface spaces |
| Open Space | Dedicated preserve area + rooftop amenities |
| Estimated Cost | $7,258,503 ($329,932/unit) |
| Timeline Constraint | Requires wellhead easement vacation (~10 years) |

Setback Scenarios by Building Height

| Height | Front | Side | Rear | Side | Net Buildable | % Parcel |
| --- | --- | --- | --- | --- | --- | --- |
| 2-story (25 ft) | 25 ft | 25 ft | 25 ft | 25 ft | 14,555 SF | 30.0% |
| 3-story (35 ft) | 35 ft | 35 ft | 35 ft | 35 ft | 11,325 SF | 23.3% |
| 4-story (40 ft) | 40 ft | 40 ft | 40 ft | 40 ft | 9,861 SF | 20.3% |

Note: RM-15 rule requires setbacks equal to building height when height exceeds minimum setback. At 3+ stories, all setbacks equal building height, severely constraining the buildable envelope.

# Section 9: Cost Estimate

11-Unit Development Cost Summary

| Category | Amount | % of Total |
| --- | --- | --- |
| Land Acquisition | $55,000 | 1.5% |
| Hard Costs (construction + site) | $3,011,125 | 79.5% |
| Soft Costs (design, engineering, permits) | $357,684 | 9.4% |
| Environmental (mitigation, studies) | $77,310 | 2.0% |
| Impact Fees | $130,207 | 3.4% |
| Financing | $155,000 | 4.1% |
| TOTAL | $3,786,326 | 100% |
| Per Unit | $344,211 |  |

22-Unit Development Cost Summary

| Category | Amount | % of Total |
| --- | --- | --- |
| Land Acquisition | $55,000 | 0.8% |
| Hard Costs (construction + site) | $6,023,688 | 83.0% |
| Soft Costs | $527,841 | 7.3% |
| Environmental | $101,560 | 1.4% |
| Impact Fees | $260,414 | 3.6% |
| Financing | $290,000 | 4.0% |
| TOTAL | $7,258,503 | 100% |
| Per Unit | $329,932 |  |

Financial Feasibility (Rental)

| Metric | Value |
| --- | --- |
| Weighted Avg Rent (11 units) | $1,575/month |
| Gross Annual Rent | $207,900 |
| Vacancy Rate | 7% |
| Effective Gross Income | $193,347 |
| Operating Expenses (40%) | $77,339 |
| Net Operating Income (NOI) | $116,008 |
| Yield on Cost | 3.06% |
| Stabilized Value (6% cap) | $1,933,467 |
| Value Gap | -$1,852,859 |

The project does NOT pencil as a rental development. Total development cost ($3.79M) exceeds stabilized value ($1.93M) by approximately 2x. For-sale condos at $275K/unit also fail to cover development costs (net revenue $2.78M vs. cost $3.79M, a $1.0M shortfall).

# Section 10: Permit Roadmap

| Permit | Agency | Timeline | Notes |
| --- | --- | --- | --- |
| PUD Preliminary Dev Plan | Palm Bay P&Z | 3-6 months | Public hearings required |
| PUD Final Dev Plan | Palm Bay P&Z | 2-4 months | After PDP approved |
| Site Plan Approval | Palm Bay DRC | 4-8 weeks | Concurrent with FDP |
| Floodplain Dev Permit | Palm Bay Building | 2-4 weeks | After BFE established |
| SJRWMD ERP | SJRWMD | 3-6 months | Longest lead item |
| Section 404 (state) | FDEP | Concurrent | Joint with ERP |
| FEMA LOMA/LOMR-F | FEMA | 60 days | Optional — if fill strategy |
| MTWCD Stormwater | MTWCD | 4-8 weeks | Concurrent with ERP |
| Building Permit | Palm Bay Building | 4-8 weeks | After all approvals |
| Utility Connections | Palm Bay Utilities | 2-6 weeks | Extension may be needed |
| Driveway Permit | Palm Bay PW | 2-4 weeks | Chapter 179 |
| HOA ARC Approval | Sandy Pines HOA | 1-3 months | CRITICAL — potential fatal |
| FWC Gopher Tortoise | FWC | 4-8 weeks | If burrows found |

Estimated Total Timeline: 18-24 months (optimistic to realistic) from project initiation to Certificate of Occupancy. Worst case: 36 months with appeals/redesign.

# Section 11: Risk Matrix

Constraint Severity Assessment — Color Coded by Risk Level

| Constraint | Severity | Coverage | Est. Cost | Timeline | Mitigation | Fatal? |
| --- | --- | --- | --- | --- | --- | --- |
| HOA CC&Rs — Multifamily Likely Prohibited | POTENTIAL FATAL | 100% | $5K legal review | 1-2 months | CC&R amendment (75% vote) or legal separation | YES |
| No Sewer/Water Service Available | HIGH | 100% | $5K-$25K extension | 2-6 months | Sewer main extension from adjacent parcel (2153) | NO |
| FEMA Zone A Flood (No BFE) | HIGH | 100% | $5K-$25K study + 17.5% premium | 6-12 weeks study | BFE determination, elevated construction, LOMA/LOMR-F | NO |
| NWI Wetland PEM1Cd (Freshwater Emergent) | HIGH | 100%* | $43K-$108K mitigation | 4-6 months ERP | Mitigation bank credits (Farmton), minimize impact | NO |
| Wellhead Protection Easement (200-ft radius) | HIGH | 47% | $0 (wait) or redesign | ~10 years | Phase 1 outside easement; Phase 2 after vacation | NO |

* NWI coverage is 100% of parcel per polygon query, but actual jurisdictional wetland boundary requires professional delineation. Partially drained (d) modifier may reduce actual jurisdictional area.

Combined Risk Assessment:

VERY HIGH. Five overlapping constraints create a "constraint stacking" effect where each issue compounds the others. The HOA CC&R constraint is potentially fatal and must be resolved first. Even if all constraints can be mitigated, the combined cost ($77K-$203K environmental + $130K-$260K impact fees + $30K-$66K permit fees) far exceeds the economic capacity of this 1.1-acre parcel.

# Section 12: Recommendation

RECOMMENDATION: HOLD / CONDITIONAL NO-GO

Primary Finding

Multifamily development on this parcel is NOT ECONOMICALLY FEASIBLE under current conditions. The combination of five overlapping constraints — HOA CC&Rs, no sewer, flood zone, wetlands, and wellhead easement — creates a development cost that exceeds the stabilized property value by approximately 2x. Environmental compliance costs alone ($77K-$203K) exceed the land value ($55K).

Immediate Actions (Cost: $0-$50)

1. Obtain CC&Rs (OR Book 3636/2327) from Brevard County Clerk. This is the #1 priority. If multifamily is prohibited, no further analysis is warranted for the intended use.

2. Obtain PUD ordinance from Palm Bay City Clerk at (321) 733-3042. This determines all permitted development standards.

3. Call Palm Bay Utilities at (321) 952-3420 to confirm sewer availability and extension costs.

Decision Framework

| Scenario | Decision | Next Step |
| --- | --- | --- |
| CC&Rs prohibit multifamily AND cannot be amended | KILL | Sell parcel or hold for alternative use |
| CC&Rs allow multifamily BUT PUD ordinance restricts density | REASSESS | Evaluate SF/townhome development |
| CC&Rs and PUD both allow multifamily | PROCEED WITH CAUTION | Commission wetland delineation and flood study ($8K-$33K) |

Alternative Strategies

Land Bank: Hold parcel for 10+ years until wellhead easement is vacated, then reassess with full parcel available. Low carrying cost (vacant land taxes ~$1,000/year).

Single-Family/Townhome: Develop 2-4 townhome units consistent with HOA character. Lower environmental impact, may avoid some constraints. Requires CC&R and PUD confirmation.

Sell: List parcel at $55K-$75K. Two consecutive tax deed sales suggest limited buyer interest, but land values in Palm Bay have been rising.

Conservation Easement: Donate development rights for tax deduction. Parcel is within NWI wetland polygon — may qualify for conservation programs.

DISCLAIMER

This report is prepared for informational purposes only and does not constitute legal, engineering, or financial advice. All cost estimates are approximate and based on publicly available data as of February 2026. Actual costs, timelines, and regulatory requirements may differ significantly. Professional consultants (licensed engineer, surveyor, environmental scientist, real estate attorney) should be engaged before making any development decisions. The analysis relies on data from BCPAO, Palm Bay GIS, FEMA NFHL, NWI, SJRWMD, and other public sources. Data accuracy is not guaranteed. CC&R and PUD ordinance review by qualified legal counsel is essential before proceeding.